## Sheet1
Risk ID | Risk Category | Risk Description | Risk Owner | Inherent Likelihood (1-5) | Inherent Impact (1-5) | Inherent Risk Score | Inherent Rating | Existing Controls | Control Effectiveness (1-5) | Residual Likelihood (1-5) | Residual Impact (1-5) | Residual Risk Score | Residual Rating | Treatment Option | Mitigation Action | Action Owner | Due Date | KRI | Status | Last Reviewed
R-001 | Cyber / IS | Due to unpatched critical vulnerabilities in the public-facing web application, there is a risk that an attacker will exploit the vulnerability to exfiltrate customer PII, which could lead to regulatory fines, remediation costs, and reputational damage. | CISO | 4 | 5 | 20 | Extreme | Quarterly vulnerability scans; WAF deployed; incident response plan in place | 2 | 3 | 4 | 12 | High | Reduce + Transfer | Implement 30-day critical-CVE patching SLA; purchase $5M cyber-liability insurance | IT Infrastructure Mgr | 2026-09-30 | Unpatched critical CVEs > 30 days | Open | 2026-06-15
R-002 | Identity & Access Management | Since offboarding utilizes manual HR-to-IT notification rather than automation, there is a risk that terminated employee VPN and Active Directory accounts continue to remain active for 48+ hours post-termination, which could lead to data exfiltration by a former employee or unauthorized access. | IT Operations Manager | 3 | 4 | 12 | High | HR termination checklist and policy that IT is notified within 24 hours of a termination occurrence. IT policy that known terminations are processed within 24 hrs. No other controls in place. | 0 | 3 | 4 | 12 | High | Reduce | Implement automated deprovisioning directly activated by the HR system's termination event which removes the manual notification step. | IT Operations Manager | 2026-08-31 | Number of terminated employee accounts active >24 hours after termination | Open | 2026-06-01
R-003 | Data Loss Prevention | Because employees do not have an approved file-sharing alternative, they might use personal cloud storage accounts to share work-related files, which could lead to customer PII being stored outside control of the company without encryption or access logs, and therefore exploitation of sensitive information by a third party could occur. | Information Security Manager | 4 | 4 | 16 | Extreme | Acceptable Use Policy prohibits use of personal cloud storage for work-related files. Policy is not enforced. | 0 | 4 | 4 | 16 | Extreme | Reduce | Implement the use of a third-party file-sharing vendor that has been vetted by the Security Team for the purpose of sharing work-related files. Implement a block on uploading to unapproved cloud storage domains. | Information Security Manager | 2026-10-15 | Number of upload attempts to unapproved cloud domains per month. | Open | 2026-06-13
R-004 | Identity & Access Management | Because MFA is optional rather than enforced for remote access and privileged accounts, there is a risk that a phishing attack harvesting a password alone can successfully compromise an account which could lead to unauthorized access to internal systems. | Identity & Access Management Lead | 4 | 5 | 20 | Extreme | MFA available but optional. Currenlt enabled voluntarily by 55% of users. | 0 | 4 | 5 | 20 | Extreme | Reduce | Implement a policy to make MFA mandatory for remote access and privileged accounts. | Identity & Access Management Lead | 2026-09-30 | % of remote access users and privileged account users. | In Progress | 2026-06-03
R-005 | Vulnerability Management | Because patch deployment for employee laptops is manual and inconsistent rather than centrally enforced, there is a risk that known vulnerabilities remian unpatched for 60+ days on some devices, which could lead to attacker exploitation. | IT Infrastructure Manager | 4 | 4 | 16 | Extreme | Patch management exists but deployment is manual per device. | 0 | 4 | 4 | 16 | Extreme | Reduce | Implement a centrally enforced deployment of patches to all employee laptops with critical vulnerabilities remediated within 15 days and high vulnerabilities within 30 days. | IT Infrastructure Manager | 2026-10-31 | Percentage of Critical/High vulnerabilities remediated within SLA (15/30 days) per month. | Open | 2026-06-14
R-006 | Third-Party | Because of critical dependency on a single cloud-hosting provider with no RTO guarantee, there is a risk that a provider outage exceeds 24 hours, which could lead to service disruption, SLA penalty fees, and reputational damage. | CTO | 3 | 5 | 15 | Extreme | Vendor SLA monitoring; basic DR plan exists | 1.7 | 2 | 5 | 10 | High | Reduce | Negotiate contractual RTO/RPO and review vendor insurance | Cloud Architect | 2026-08-15 | Vendor SLA breach count | In Progress | 2026-06-06
R-007 | Third-Party/Vendor Risk | Because vendor access reviews are not completed on a regular schedule, there is a risk that third-party contractors retain access to internal systems after engagement ends, which could lead to an expanded attack surface via accounts that are not actively monitored. | Vendor Risk Manager | 3 | 4 | 12 | High | Vendor access is granted upon engagement; no formal offboarding or periodic review process. | 0 | 3 | 4 | 12 | High | Reduce | Implement conditional access for vendors that has an automatic expiration date when the contract ends. Implement quarterly vendor recertification requiring Vendor Risk Management sign-off. | Vendor Risk Management | 2026-10-25 | Number of vendor accounts with active access beyond their contract end date. | Open | 2026-06-20
R-008 | Detection & Response | Because logging is enabled inconsistently across cloud and on-prem systems, there is a risk that security incidents go undetected for extended periods, which could lead to delayed incident containment and increased breach scope. | SOC Manager | 4 | 5 | 20 | Extreme | Logging is enabled on core network infrastructure; cloud workload logging inconsistent. | 0 | 4 | 5 | 20 | Extreme | Reduce | Extend centralized SIEM ingestion to all cloud and on-prem systems, with a defined minimum logging baseline (authentication, privilege escalation, and data access events) applied to all new systems at provisioning, and automated alerting configured for high-risk event patterns | SOC Manager | 2026-11-28 | % of cloud and on-prem systems that are included in logging practices. | In Progress | 2026-07-01
R-009 | Business Continuity | Because of the data center’s location in a flood-prone zone with aging backup-power infrastructure, there is a risk that a severe weather event disables the primary data center for a significant timeframe, which could lead to failure to meet the RTO on critical services and SLA penalty payments. | CIO | 2 | 5 | 10 | High | DR plan exists; annual tabletop exercise conducted; offsite backups | 1 | 2 | 4 | 8 | Medium | Reduce | Upgrade backup generators; contract secondary hot-site; conduct live DR exercise by Q3 | IT Operations Mgr | 2026-08-25 | DR exercise success rate (%) | Open | 2026-05-18
R-010 | IT Governance | Because employees can sign up for free-tier SaaS tools without IT/security review, there is a risk that unvetted applications with unknown security postures end up processing company data, which could lead to data exposure outside any approved vendor risk assessment. | IT Governance Manager | 4 | 5 | 20 | Extreme | Acceptable Use Policy refers to an approved software list, but there is no technical enforcement — nothing actually stops someone from signing up for a new SaaS tool with a work email. | 0 | 4 | 5 | 20 | Extreme | Reduce | Deploy a SaaS discovery tool to detect unsanctioned application usage across the network, paired with a defined intake process allowing employees to request new tool approval within a 5-business-day SLA | IT Governance Manager | 2026-07-20 | Number of unaproved application discoveries per month. | Open | 2026-05-05